## Folha1
| March |  | April |  |  |  | May |  |  |  |  | June
Task | 4w | 5w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 5w | 1w | 2w | 3w | 4w | 5w
Gameplay Focus | bar: March 5w to May 1w
Create code arquithecture | bar: March 5w
Character deck | bar: April 1w
Character hand | bar: April 1w
Character play cards | bar: April 2w
Enemy placement | bar: April 2w
Enemy attacks | bar: April 3w
Complete turn-based | bar: April 4w
Simple UI | bar: April 4w
Status Effect Mechanic | bar: April 4w to May 1w
Procedural Generation | bar: April 4w to May 5w
World Generation | bar: May 1w
Stage Loader | bar: May 2w to May 3w
Reward System | bar: May 4w to May 5w
UI | bar: May 5w to June 3w
Main Screen | bar: May 5w
Main Menu | bar: May 5w
Gameplay UI | bar: June 1w
Procedural UI | bar: June 2w
Extras | bar: June 3w
Final Report | bar: May 1w to June 5w
Polishing bug fixing | bar: June 2w to June 4w
Save/Load | bar: June 3w to June 4w
Deploy | bar: June 5w